## Master template
Pre-Launch Multi-Site Marketing Checklist |  | Live date:
A template to start your marketing planning and alignment. |  | Kick off date:
Complete these columns yourself
Phase & Timeline | Milestone / Task | Key Focus | Owner (Name) | Deadline (Date) | Completed? (Y/N) | Link to reference
Phase 1: Commercial Alignment | Project Kick off with All Stakeholders | Aligning core team, ownership and communciation channels. |  |  | ✅
| Define Site-Level Unit Economics | Establish clear occupancy, yield, and target CAC thresholds. |  |  | ❌
(T-Minus 6 to 4 Months) | Internal Launch | Build excitement and support internally for new site.
| Teaser Campaign | Tease the new site on social channels and newsletter updates.
| Conduct Local Market Research | Analyse regional competitors, pricing models, and positioning gaps.
| Map the Ideal Persona | Tailor buyer profiles to regional demographics (e.g. enterprise vs scale-ups).
| Establish Joint Sales & Marketing KPIs | Agree weekly pipeline velocity metrics with the commercial team.
| Agree Project Updates Cadence & Schedule | Planning update meetings and relevant attendees.
Phase 2: Technical & Data Setup | Build Site-Specific Digital Architecture | Set up dedicated landing pages optimised for regional search intent.
| Set Up Local Search & Citation Assets | Claim and optimise Google Business Profiles and regional map pins.
(T-Minus 4 to 2 Months) | Integrate CRM & Local Data Loops | Ensure local lead routing, automated follow-ups, and attribution work.
| Update all Collateral with Site Listings | Refreshing brochures, ads, business information and presentations.
| PR Launch | Engage sector press around opening and ongoing growth plans.
| Launch Awareness Advertising | Targeting PPC, Programmatic, Paid Social and Print to promote upcoming opening.
| For B2B and partner activity establish ABM Data Infrastructure | Build a target account list of businesses within an appropriate radius.
Phase 3: Hyper-Local Demand Gen | Deploy Targeted Pre-Leasing Campaigns | Launch hyper-local paid search and targeted social campaigns.
| Set up Email Nurture & Existing Database | Sending updates to engaged audience with special offers and behind the scenes.
(T-Minus 2 Months to Launch) | Activate Regional B2B Partnerships | Engage with local brokers, business networks, and chambers.
| Execute High-Intent Direct Outreach | Initiate tailored outbound campaigns to the pre-mapped ABM target list.
| Host Hard-Hat Tours & Preview Events | Run exclusive, low-friction preview walkthroughs for corporate prospects & press.
| Opening / Launch Party | Distribute invites and event planning for new site opening.
| Soft Launch Pricing Incentives and Offers | Maximising early revenue and driving footfall from promotions and early pricing.
Phase 4: Launch & Stabilisation | Align Local Ops with Brand Promise | Ensure on-site teams are briefed on campaign messaging and lead handling.
| Run Weekly Pipeline Reviews | Review sales/marketing data loops every 7 days against occupancy/revenue goals.
(Launch to Month 3) | Capture Early Social Proof | Secure testimonials, site photos, videos and case studies from early customers to feed ongoing channels.
| Transition to Baseline Retention & Growth | Shift focus from launch velocity to sustained presence and referral schemes.
| Project Learnings and Refinement | Capture effective channels, process and templates for future openings.